BULKSCRUBS DIRECT

Website Materials Request

Everything needed from BulkScrubs Direct to build and launch the website, sequenced by when each item is actually required.

| Field | Detail |
| --- | --- |
| Prepared for | BulkScrubs Direct |
| Prepared by | Christian — Website Development |
| Date | 2 September 2026 |
| Source | Updated Website Materials & Business Requirements, Section 14 |
| Website build | Version 1 — approximately 14 weeks from start |

About this document

This is not a list of new requirements. Section 14 of your requirements document already lists the materials still to be supplied; this document takes that same list, adds the few items that were not covered, and sequences everything by when it is genuinely needed.

The build itself is not held up by most of this. Development can begin immediately and run for several weeks on placeholder content. What these materials affect is the end of the project — if they arrive late, the work finishes and then waits, which is the most common way a project like this slips past its date.

Two items are worth acting on this week regardless of anything else, because their timing is outside everyone’s control: the payment merchant account (approval takes weeks) and DNS access for email setup (propagation takes days).

How to use this Sections 1 to 7 each carry a deadline and a plain statement of what that item blocks. Where a decision is needed rather than a file, a recommended default is given — if the default is acceptable, simply confirm it and no further thought is required. Anything left unanswered by its deadline will proceed on the stated default, and the assumption will be recorded in writing.

①   Summary — everything, by deadline

Ordered by when each item blocks work. Items in bold are the ones that stop launch entirely.

| When | What is needed | What it blocks if late |
| --- | --- | --- |
| Week 1 | Four decisions (Section 2) | Database structure, cart behaviour, all of checkout |
| Week 1 | Payment merchant account opened | All payment work — approval has weeks of lead time |
| Week 1 | Stallion Express account + API key | Automatic shipping rate calculation |
| Week 1 | Domain / DNS access | Order and account emails reaching inboxes |
| Week 2–3 | Final logo file | Website header, emails, invoices, favicon |
| Week 2–3 | Business email address and phone number | Contact page, email sender identity |
| Week 4–5 | Product photography | Everything visual — the design is photography-led |
| Week 4–5 | Product names, SKUs, colours, sizes, descriptions | The real product catalogue |
| Week 6–7 | Three wholesale tiers — thresholds and prices | Wholesale pricing cannot be configured |
| Week 8–10 | Confirmed tax provinces + GST/HST number | Correct tax collection |
| Week 8–10 | Pickup address, hours, lead time | Local pickup option |
| Week 8–10 | Shipping rates (if not using live calculation) | Shipping charges at checkout |
| Week 11–12 | Returns, shipping, privacy and terms wording | Launch — this is a legal blocker |
| Week 12–13 | Opening stock quantities and product weights | Stock accuracy and shipping rates |
| Week 12–13 | Social media links | Website footer |

②   Four decisions needed before development starts

These four shape the database and cannot be changed cheaply later. Each has a recommended default — confirming the default is a complete answer.

Decision 1 — What exactly is a scrub set?

The requirements price “approximately $65 per scrub set” but do not define what a set is. The question that matters: when a customer buys a set, do they choose

one size for both pieces, or do they choose a top size and a bottom size separately? Many scrubs buyers need different sizes for each.

Why it matters: this determines how every product, SKU and stock count is structured. Changing it after the catalogue is loaded means rebuilding all of it.

Recommended default: top and bottom sized separately. It covers the simpler case as well, so it is the safer choice if there is any doubt.

☐   Confirm the recommended default (top and bottom sized separately)

☐   One size applies to the whole set

☐   Tops and bottoms are also sold individually, not only as sets

Notes:  ______________________________________________________________

Decision 2 — Does a shopper without an account get wholesale pricing?

The requirements state that wholesale prices are hidden until someone signs in, and also that reaching the minimum order value is what qualifies a customer. Taken together, a shopper with no account who fills a $200 cart has technically qualified — which would make the sign-in step pointless and remove any reason to register.

Recommended default: an account is required for wholesale pricing to be applied. A qualifying shopper without an account sees “Your order qualifies for wholesale — sign in to save $118”, and the discount applies the moment they register. This is how Faire works, and it makes signing up worth something at the exact moment the customer most wants to.

☐   Confirm the recommended default (account required to receive wholesale pricing)

☐   No — anyone reaching the threshold should get wholesale pricing, account or not

Notes:  ______________________________________________________________

Decision 3 — Are the wholesale tiers based on dollars or on quantity?

The requirements use “minimum order quantity” and “qualifying order value” interchangeably, but they behave differently. A $200 spend threshold lets someone buying four expensive sets qualify while someone buying five cheaper sets does not. A 10-unit threshold is predictable for the buyer and unaffected by future price changes.

Recommended default: support both, so a tier can be reached by either spending enough or buying enough. This is the most generous to the customer and means the rule can be changed later from the admin dashboard rather than by rebuilding anything.

☐   Confirm the recommended default (either dollar value or unit quantity qualifies)

☐   Dollar value only

☐   Unit quantity only

Notes:  ______________________________________________________________

Decision 4 — Which payment processor?

This needs starting in week 1 regardless of the answer, because merchant account approval takes weeks and is outside our control.

Recommended default: Stripe. A single integration covers Visa and Mastercard, Apple Pay and Google Pay, and PayPal in Canadian dollars. Card details never touch the BulkScrubs Direct website or database. Instalment options such as Affirm or Klarna can be switched on later from a dashboard setting rather than requiring new development — which is what the requirements ask for.

Canadian alternatives such as Moneris or Helcim may offer slightly lower card processing fees, but have weaker developer tooling and no single-integration path to instalment payments.

☐   Confirm Stripe

☐   Prefer a Canadian processor — please advise on Moneris / Helcim

Notes:  ______________________________________________________________

Related question — is Interac e-Transfer wanted at launch?

There is no practical automated e-Transfer integration available at this business size. It can still be offered, but it works differently: the order is placed and held as “Pending Payment”, the customer is emailed transfer instructions, and a staff member marks the order as paid once the funds arrive. Stock is held in the meantime.

☐   Yes — offer e-Transfer at launch

☐   No — card and PayPal only

If yes, we need: the e-Transfer email address, and how long an unpaid order should be held before it is automatically cancelled (recommended: 3 business days).

e-Transfer address / hold period:  ______________________________________________________________

③   Brand and contact details

Needed by week 2–3. These appear across the website, emails and invoices, so they are awkward to change once everything is built.

| Item | Format needed | Used for |
| --- | --- | --- |
| Logo — primary | Vector preferred (.svg, .ai, .eps). High-resolution .png otherwise, on transparent background, at least 1000px wide | Website header, invoices, emails |
| Logo — icon only | Square version of the mark, if one exists | Browser tab icon, social sharing |
| Business email address | The address customers should reply to | Contact page, all outgoing email |
| Business phone number | With preferred hours if applicable | Contact page, order confirmations |
| Business mailing address | Full address | Invoices, tax records, policy pages |
| Social media links | Full URLs for any active accounts | Website footer |
| Brand guidelines | If any exist — fonts, colours, usage rules | Matching the site to existing brand |

If no brand guidelines exist That is completely normal, and nothing is held up by it. A design direction has already been prepared based on the Faire-style reference supplied — warm off-white backgrounds, refined typography, and product photography carrying the colour. Those choices become the BulkScrubs Direct brand by default, so they are worth a look before the build begins.

④   Product catalogue

Needed by week 4–5. The single largest item on this list, and the one worth starting earliest.

4.1  Product data

A spreadsheet is the easiest format — one row per colour-and-size combination. The columns below match how the website stores products, so a well-filled spreadsheet can be imported directly rather than typed in by hand.

| Column | Example | Required |
| --- | --- | --- |
| Product name | Classic Scrub Set | Yes |
| Category | Women's Scrubs / Men's Scrubs | Yes |
| Base SKU | BSD-CSS | Yes |
| Colour name | Ceil Blue | Yes |
| Size | XS / S / M / L / XL / 2XL / 3XL | Yes |
| Variant SKU | BSD-CSS-CEIL-M | Yes — must be unique |
| Retail price (CAD) | 65.00 | Yes |
| Opening stock quantity | 24 | Yes — can follow later |
| Weight (grams) | 480 | See 4.3 below |
| Photo filenames | ceil-front.jpg, ceil-back.jpg | Yes |
| Description | Full product description | Yes |
| Materials | 55% cotton, 45% polyester | Yes |
| Dimensions & fit | Fit notes, inseam, length | Yes |

A blank spreadsheet with these columns can be supplied on request — just ask.

4.2  Product photography

The website design is photography-led. The reference style supplied uses large, clean product images with generous white space, and the product images carry essentially all of the colour on the page. Weak photography will undermine the design more than any other single factor.

Per product: at least 3 images (front, back, detail); 5 or more is better

Per colour: one image showing each colour, so the gallery can switch when a shopper picks a colour

Resolution: minimum 2000 × 2000 pixels, square or 4:5 portrait, consistent framing across all products

Background: plain white or light neutral, consistent across the range

Format: .jpg or .png, named to match the spreadsheet (e.g. ceil-front.jpg)

4.3  Product weights — not on the original list

This item was not in Section 14, but automatic shipping calculation is impossible without it.

If the website is to calculate shipping automatically at checkout, it needs to know how much each parcel weighs. Without weights, shipping rates would have to be fixed amounts set manually.

There is a shortcut. A 3XL top weighs perhaps 150–200 grams more than an extra-small, which is usually well inside the same shipping price band. So rather than weighing every single size, one average weight per product is normally accurate enough — which reduces this from hundreds of measurements to a handful.

☐   We hold stock and can weigh a sample of each product

☐   Products come from a supplier — we will request specification sheets

☐   Weights are not available — please use fixed shipping rates instead

Notes:  ______________________________________________________________

⑤   Wholesale pricing — the three tiers

Needed by week 6–7. This is the commercial heart of the website.

The requirements give $200 as an opening minimum and roughly $45 per set as a wholesale reference price, with final tiers to follow. Those final numbers are needed to configure the pricing system. All of these remain editable from the admin dashboard afterwards — nothing here is permanent.

| Tier | Qualifies at (CAD) | or at (units) | Price per set (CAD) | or discount (%) |
| --- | --- | --- | --- | --- |
| Tier 1 | $200 |  | $ | % |
| Tier 2 | $ |  | $ | % |
| Tier 3 | $ |  | $ | % |

Fill in either a price per set or a percentage discount — whichever is easier to think about. Both work.

A related question

Should wholesale pricing be a straight percentage off across the whole catalogue, or a specific price set per product? A percentage is far less work to maintain as the catalogue grows; specific prices give exact control. Both are supported, and individual products can override a catalogue-wide percentage where needed.

☐   A percentage discount per tier, applied across the catalogue

☐   A specific wholesale price for each product

Notes:  ______________________________________________________________

Free shipping threshold

The requirements target free shipping on orders over $600. Please confirm, and note that because this sits above the $200 wholesale minimum, wholesale customers will reach it routinely.

☐   Confirm $600

Different amount:  ______________________________________________________________

⑥   Shipping, pickup and tax

Needed by week 8–10.

6.1  Shipping

Stallion Express: Account login and API key. Without these, automatic rate calculation cannot be built or tested.

Service selection: Should customers see a choice of shipping speeds, or a single rate? (Recommended: cheapest option plus one faster option.)

Fallback rates: If automatic calculation is not used, a table of shipping prices by destination and order size is needed instead.

6.2  Local pickup

| Item | Detail needed |
| --- | --- |
| Pickup address |  |
| Pickup hours |  |
| How long before an order is ready |  |
| Any restrictions (order size, region) |  |

6.3  Canadian tax

This one needs your accountant, not your developer. The website can calculate tax correctly for every province, but only BulkScrubs Direct can say which taxes it is registered to collect. Charging a tax you are not registered for, or failing to charge one you are, is a compliance problem no amount of code can solve.

GST/HST registration number: required for invoices and receipts

GST/HST: confirm GST/HST is collected on all Canadian destinations

Provincial sales tax: are you registered to collect PST in British Columbia, Saskatchewan or Manitoba?

Quebec: are you registered to collect QST in Quebec?

Default if unconfirmed: GST/HST collected on all destinations, Ontario HST at 13%, with provincial and Quebec taxes switched off until registration is confirmed.

⑦   Policy wording — the launch blocker

Needed by week 11–12. Of everything on this list, this is the item most likely to hold up launch.

Four policies are required before the website can accept payments: returns and refunds, shipping, privacy, and terms and conditions. These need to come from BulkScrubs Direct — a lawyer, or a reputable policy service. They cannot be written by the developer, because they are legal commitments the business is bound by.

Why this slips, and how to avoid it The writing is rarely the slow part — the decisions behind it are. The checklist below is every decision the four policies actually need. Answering these takes perhaps an hour; once answered, a lawyer or policy service can produce the wording quickly. Leaving it until week 11 to start thinking about is what causes the delay.

7.1  Returns and refunds — decisions needed

☐   How many days does a customer have to return an item?

☐   What condition must it be in? (unworn, tags attached, original packaging)

☐   Who pays return shipping — customer or BulkScrubs Direct?

☐   Is there a restocking fee? If so, how much?

☐   Are refunds issued to the original payment method, or as store credit?

☐   Which items, if any, are final sale?

☐   How are faulty or incorrectly shipped items handled differently?

The one that matters most: do wholesale orders have different return terms from retail orders? A customer returning fifty sets is a very different commercial risk from one returning a single set, and most wholesale sellers treat the two differently. If the policy does not distinguish them, the more generous retail terms apply to bulk orders by default.

Wholesale return terms:  ______________________________________________________________

7.2  Shipping policy — decisions needed

☐   How long between an order being placed and being dispatched?

☐   Estimated delivery times by region

☐   Which carriers are used

☐   What happens if a parcel is lost or arrives damaged?

☐   Do you ship outside Canada? (Assumed no at launch)

7.3  Privacy policy — decisions needed

Canadian privacy law (PIPEDA) applies. The policy must cover:

☐   What customer information is collected and why

☐   Which third parties receive it (payment processor, shipping carrier, email service)

☐   How long information is kept

☐   Who a customer contacts to access or delete their information

☐   Cookie usage — including any future analytics or advertising tools

7.4  Terms and conditions — decisions needed

☐   Governing law (Ontario, Canada is assumed)

☐   What happens if a price is displayed incorrectly

☐   Grounds for suspending or closing a customer account

☐   Limitation of liability

☐   Whether wholesale purchases carry any additional terms

⑧   Accounts to open — in the BulkScrubs Direct name

Needed in week 1 where marked.

Your requirements state that BulkScrubs Direct should ultimately own and control the domain, hosting, website data, payment accounts and third-party services. The most reliable way to achieve that is for every account to be opened by BulkScrubs Direct from the beginning, with developer access added as a collaborator — rather than opened by the developer and transferred later. Transfers get forgotten; ownership from day one does not.

| Account | Who opens it | When | Notes |
| --- | --- | --- | --- |
| Payment processor | BulkScrubs Direct | Week 1 | Approval takes weeks — start immediately |
| Domain / DNS | BulkScrubs Direct | Week 1 | Developer needs access to configure email |
| Stallion Express | BulkScrubs Direct | Week 1 | API key required for shipping rates |
| Server hosting | BulkScrubs Direct | Week 1 | Canadian region recommended |
| Email delivery service | BulkScrubs Direct | Week 1–2 | For order and account emails |
| Cloud file storage | BulkScrubs Direct | Week 2 | Product images and backups |

⑨   What happens if items arrive late

Stated plainly so there are no surprises, and so priorities can be set deliberately rather than discovered at the end.

| If this is late | Consequence |
| --- | --- |
| Policy wording | Launch is blocked.** The website cannot responsibly take payments without published returns, shipping, privacy and terms policies. |
| Payment merchant account | Launch is blocked.** Approval time is outside anyone’s control, which is why it must start in week 1. |
| Product photography | Launch is effectively blocked.** The design depends on it; placeholder images cannot go live. |
| Wholesale tier numbers | Launch is blocked.** Wholesale pricing is the core feature and cannot be configured without them. |
| Product data and stock | Launch delayed. The catalogue can be loaded quickly once supplied, but nothing can be sold before it is. |
| Product weights | Not blocking. Falls back to fixed shipping rates set manually, which may be less accurate and cost more per order. |
| Stallion API key | Not blocking. Falls back to fixed shipping rates; live rates can be enabled later. |
| Logo | Not blocking during the build, but it appears in so many places that supplying it late means revisiting many of them. |
| Social links | Not blocking. The footer simply omits them until supplied. |
| Tax registration confirmation | Not blocking technically, but launching with incorrect tax settings creates a compliance exposure. |

⑩   Returning this document

The fastest route is to work through Section 2 first — those four decisions unblock the most work and several can be answered simply by confirming the recommended default. Everything else can follow at the pace set out in Section 1.

Answers can be returned as marked-up copies of this document, by email, or discussed in a call and recorded afterwards — whichever is easiest. Anything unanswered by its deadline will proceed on the stated default and the assumption will be confirmed in writing.

Questions about anything in this document are welcome at any point — including “why do you need this?”